## State Timelines (to June 5 205)
| Challenge Process (CP) |  |  |  |  | Subgrantee Selection |  |  |  | Final Proposal
State | CP Status | Challenges | Rebuttals | Adjudication | Results OK'd? | Date V2 Approved | Pre-Qual | Round 1 | Round 2 | Draft Released | Approved
Alabama | Emerging | 8/1-8/31 | 9/16-10/16 | 10/17-11/16 | No | 2024-10-17 | 12/6/24 - 1/24/25 | 4/7/25 - 5/22/25
Alaska | Ongoing | 5/6-6/4 | 6/5-7/5 | 7/6-8/4 | No | 2024-10-11 | n/a | 10/13/25 - 12/11/25 [est.]
Arizona | Ongoing | 3/15-5-14 | 3/15-5/30 | 5/15-6/30 | No | 2024-08-05 | 11/4/24 - 6/30/25 | 1/6/25 - 3/7/25 | 6/3/25 - 7/18/25
Arkansas | Ongoing | 3/20-4/19 | 4/20-5/20 | 5/21-6/20 | No | 2024-09-30 | 7/8/24 - 12/27/24 | 1/7/25 - 1/21/25 | 2/24/25 - 3/11/25
California | Ongoing | 7/8-8/6 | 8/21-9/19 | 9/20-10/19 | No | 2024-10-04 | 3/25/25 - 5/1/25 | 4/2/25 - 5/9/25
Colorado | Closed | 1/10-2/9 | 2/10-3/11 | 3/12-4/11 | Yes | 2024-06-03 | n/a | 9/12/24 - 10/28/24 | 1/27/25 - 2/28/25
Connecticut | Ongoing | 4/1-5/14 | 5/24-6/22 | 6/23-7/22 | No | 2024-07-18 | 10/21/24 - 11/22/24 | 1/27/25 - 2/25/25
Delaware | Closed | 1/17-2/16 | 2/17-4/1 | 4/2-5/2 | No | 2024-05-02 | 6/13/24 - 7/9/24 | 9/20/24 - 10/25/24 |  | 2024-12-11 | 2025-01-14
Florida | Emerging | 7/22-9/5 | 9/14-10/30 | 9/16-12/13 | No | 2024-10-17 | 5/5/25 - | 2025-07-01
Georgia | Closed | 3/4-4/2 | 4/3-5/2 | 5/6-6/4 | No | 2024-09-26 | n/a | 12/2/24- 1/30/25
Hawaii | Emerging | 8/19-9/18 | 9/30-10/30 | 11/1-11/30 | No | 2024-07-16 | n/a | 11/25/24 - 1/31/25
Idaho | Ongoing | 6/3-7/1 | 7/15-8/11 | by 10/1 | No | 2024-09-12 | 1/15/25 - 2/14/24 3/13/25 - 3/27/25 [reopened]
Illinois | Closed | 2/27-3/18 | 4/16-5/6 | 5/7-6/18 | No | 2024-06-13 | 6/17/24 - 7/23/24 | 1/23/25 - 2/26/25 | 5/27/25 - 7/16/25
Indiana | Ongoing | 3/4-5/17 | 5/2-6/1 | 6/2-7/1 | No | 2024-07-08 | 8/26/24 - 9/27/24 | 12/30/24 - 2/12/25
Iowa | Ongoing | 5/15-6/13 | 6/14-7/28 | 6/14-7/28 | No | 2024-09-25 | n/a
Kansas | Closed | 12/14-1/14 | 1/26-2/9 | March | Yes | 2024-04-25 | 5/13/24 - 12/20/24 | 10/21/24 - 12/20/24
Kentucky | Ongoing | 5/6-6/3 | 6/4-7/1 | 7/2-8/30 | No | 2024-06-17 | 8/14/24 - 9/13/24 2/11/25 - 3/13/25 | 1/15/25 - 3/15/25
Louisiana | Closed | 10/6/23 - 11/5/23 | 11/8/23 - 12/8/23 | 12/9/23 - 1/4/24 | Yes | 2023-12-07 | 7/1/24 - 7/14/24 | 8/15/24 - 8/29/24 | 9/11/24 - 9/25/24 | 2024-11-18 | 2025-01-13
Maine | Ongoing | 4/26-5/31 | 6/7-7/2 | 7/8-8/2 | No | 2024-06-17 | 9/18/24 - 10/18/24 | 1/17/25 - 3/7/25
Maryland | Emerging | 7/16-9/8 | 9/11-10/10 | 10/11-11/10 | No | 2024-07-10 | 2/28/25 - 3/14/25
Massachusetts | Ongoing | 6/20-7/20 | 7/26-8/25 | 8/26-10/18 | No | 2024-07-25 | 9/26/24 - 10/28/24 | 1/15/25 - 3/10/25
Michigan | Ongoing | 3/25-5/3 | 5/4-6/13 | 6/14-7/14 | No | 2024-08-28 | 6/28/24 - 3/10/25 | 1/9/25 - 4/9/25
Minnesota | Emerging | 7/22-8/21 | 8/22-9/20 | 9/21-10/21 | No | 2024-09-26 | 1/27/25 - 3/13/25 | 3/24/25 - 4/21/25
Mississippi | Emerging | 8/1-9/4 | 9/18-10/7 | by 11/1 | No | 2024-08-29 | 11/18/24 - 12/13/24 | 5/15/25 - 6/29/25
Missouri | Ongoing | 4/25-5/8 | 5/9-6/7 | 6/8-7/7 | No | 2024-08-02 | 7/3/24 - 2/5/25 4/7/25 - 6/3/25 [for Rd. 2] | 12/5/24 - 2/20/25 2/21/25 - 3/23/25 [sub-round 1]
Montana | Closed | 1/16-2/15 | 2/19-3/20 | 3/25-4/24 | Yes | 2024-08-01 | 3/12/24 - 10/1/24 | 8/13/24 - 10/15/24
Nebraska | Closed | 3/15-4/14 | 4/15-5/15 | 5/16-6/15 | No | 2024-09-18 | 2/7/25 - 3/9/25 | 4/1/25 - 5/16/25
Nevada | Ongoing | 2/27-3/28 | 3/29-5/9 | 5/10-6/9 | No | 2024-04-17 | 8/12/24 - 10/7/24 | 8/26/24 - 10/10/24 |  | 2024-12-17 | 2024-01-17
New Hampshire | Emerging | 7/15-8/14 | 8/30-9/29 | 9/30-10/30 | No | 2024-06-05 | 11/22/24 - 3/1/25 | 1/6/25 - 3/1/25
New Jersey | Emerging | 11/4/24 - 1/3/25 | 1/11/25 - 2/9/25 | 2/10/25 - 3/17/25 | No | 2024-09-06 | 4/14/25 - 6/6/25 | 4/14/25 - 6/19/25
New Mexico | Ongoing | 4/18-5/18 | 6/3-7/3 | 7/4-8/3 | No | 2024-07-26 | 9/16/24 - 11/15/24 5/9/25 - 5/30/25 [for Rd. 2] | 1/3/25 - 3/24/25
New York | Ongoing | 3/19-4/18 | 5/2-6/1 | 6/2-7/2 | No | 2024-08-13 | 6/6/24 - 9/30/24 | 12/13/24 - 2/7/25 Reopened for select PAs - 3/5/25 - 3/28/25 For Alt Tech - 4/15/25 - 5/12/25
North Carolina | Fall 2024 | 9/3/24 - 1/8/25 | 1/21/25 - 2/20/25 | 2/21/25 - 3/22/25 | No | 2024-10-03 | 9/16/24 - 2/3/25 5/30/25 - 6/30/25 [reopened]
North Dakota | Ongoing | 4/18-5/19 | 5/19-6/18 | 6/18-7/18 | No | 2024-09-12 | Until 11/19/24 [optional] | 11/22/24- 1/17/25 | 4/7/25 - 5/9/25
Ohio | Ongoing | 5/28-7/5 | 7/22-8/12 | 8/13-9/11 | No | 2024-10-11 | TBA
Oklahoma | Forthcoming | 9/23/23 - 10/23/24 | 10/29/24 - 11/28/24 | 11/30/24 - 1/15/25 | No | 2024-08-01 | 1/30/25- 4/30/25 | 4/21/25 - 5/26/25
Oregon | Ongoing | 4/22-5/22 | 5/30-6/29 | 6/30-8/24 | No | 2024-06-13 | 2/12/25 - 3/14/25 | 4/22/25 - 5/22/25 [paused as of 5/12/25]
Pennsylvania | Ongoing | 4/24-5/23 | 5/24-6/23 | 6/24-7/24 | No | 2024-05-06 | n/a | 11/22/24 - 2/7/25
Rhode Island | Ongoing | 5/29-7/6 | 7/7-8/6 | 8/7-9/6 | No | 2024-07-17 | n/a | 3/31/25 - 5/9/25
South Carolina | Ongoing | 4/15-5/14 | 5/15-6/14 | 6/15-7/14 | No | 2024-09-26 | 11/12/24 - 1/6/25
South Dakota | Ongoing | 5/15-6/14 | 5/15-7/14 | 8/6-9/5 | No | 2024-08-29 | n/a | 3/3/25 - 4/4/25
Tennessee | Ongoing | 5/7-6/1 | 6/2-7/17 | 6/27-7/21 | No | 2024-08-02 | 8/9/24 - 10/23/24 | 11/1/24 - 1/24/25 [Qualification applications] 3/10/25 - 4/18/25 [PAU applications]
Texas | Emerging | 12/3/24 - 12/17/24 | 1/10/25 - 1/24/25 | Spring 2025 | No | 2024-11-19 | 3/17/25 - 5/14/25 | 6/12/25 - 8/1/25
Utah | Ongoing | 4/18-5/28 | 5/29-7/8 | 7/9-8/8 | No | 2024-07-22 | 10/22/24 - 12/21/24 | 2/10/25 - 4/25/25
Vermont | Ongoing | 3/18-4/1 | 4/15-4/29 | 4/29-5-22 | No | 2024-08-01 | 12/3/24 - 1/9/25 | 3/6/25 - 4/16/25
Virginia | Closed | 11/1/23 - 12/1/23 | 12/2/23 - 1/16/24 | 1/17/24 - 2/16/24 | No | 2024-07-26 | 10/1/24 - 11/30/24 | 12/1/24 - 3/1/25
Washington | Ongoing | 4/15-5/14 | 4/15-6/23 | 6/24-8/3 | No | 2024-05-09 | n/a | 11/12/24 - 1/31/25
West Virginia | Closed | 2/10-3/10 | 3/11-4/9 | 4/10-5/9 | Yes | 2024-04-26 | 3/18/25 - 5/30/25 | 8/26/24 - 10/26/24; Reopened 11/13/24 - 12/19/24
Wisconsin | Ongoing | 4/29-5/29 | 6/20-7/20 | 7/21-8/20 | No | 2024-07-29 | 8/1/24 - 10/1/24 | 1/13/25 - 2/25/25 | 5/8/25 - 5/29/25
Wyoming | Ongoing | 5/20-6/19 | 7/1-7/30 | 7/31-8/29 | No | 2024-08-08 | 8/15/24 - 9/14/24; Reopened 10/9/24 -10/16/24 | 10/21/24 - 1/24/25
Note on B1: Approximate timelines based on approved V1s and/or descriptions on SBO websites
Note on C2: All dates in 2024 unless otherwise noted
Note on D2: All dates in 2024 unless otherwise noted
Note on E2: All dates in 2024 unless otherwise noted
Note on G2: Dates primarily correspond with when NTIA announced the approval via news release. Actual approval date might vary by a week or so. In April 2025, NTIA issued a blanket waiver extending the deadline for filing Final Proposals (the initial date for which was 365 days from V2 approval) by 90 days.
Note on C35: Extended b/c of Hurricane

## State Timelines (June 6 on)
|  | ULFW |  | Pre-Qualification |  | Benefit of the Bargain Round |  | Public Comment Period for Final Proposal |  | Updated Pre-Qual List
State | Final Proposal Due | Notice Issued | Final Decision | Re-Opened | Closes | Opens | Closes | Opens | Closes
Alabama | 2025-09-16 | 2025-06-12 |  | 2025-06-20 | 2025-06-30 | 2025-07-01 | 2025-07-15 |  |  | Link
Alaska | 2025-10-01 | 2025-06-11 |  | n/a | n/a | 2020-07-03 | 2025-08-03
Arizona | 2025-09-04 | 2025-06-13 |  | [already open] | 2025-06-30 | 2025-07-08 | 2025-07-22 | 2025-08-25 | 2025-09-01 | Link
Arkansas | 2025-09-04 | 2025-06-11 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-07 | 2025-07-14 |  |  | Link
California | 2025-11-21 | 2025-06-18 |  | 2025-07-11 | 2025-07-17 | 2025-07-19 | 2025-08-02
Colorado | 2025-09-04 | 2025-06-16 |  | n/a | n/a | 2025-07-07 | 2025-07-21
Connecticut | 2025-09-16 | 2025-06-18 |  |  |  | 2025-07-11 | 2025-07-22 | 2025-09-09 | 2025-09-16 | Link
Delaware | 2025-09-04 | 2025-06-13 |  | 2025-06-25 | 2025-07-05 | 2025-07-08 | 2025-07-18
Florida | 2025-10-03 |  |  |  |  | 2025-07-14 | 2025-08-04
Georgia | 2025-09-04 |  |  | 2025-06-16 | 2025-06-25 | 2025-06-30 | 2025-07-14
Hawaii | 2025-09-04 | 2025-06-26 |  | 2025-07-11 | 2025-07-18 | 2025-07-11 | 2025-08-01
Idaho | 2025-09-25 | 2025-06-17 |  | 2025-07-15 | 2025-07-19 | 2025-07-15 | 2025-07-29 |  |  | Link (old)
Illinois | 2025-09-30 | 2025-06-11 |  |  |  | 2025-07-01 | 2025-07-18 | 2025-08-28 | 2025-09-04
Indiana | 2025-09-19 | 2025-06-12 |  | 2025-06-20 | 2025-07-21 | 2025-07-10 | 2025-07-28 | 2025-08-27 | 2025-09-02
Iowa | 2025-09-04 | 2025-06-17 |  | n/a | n/a | 2025-07-16 | 2025-07-30 | 2025-08-25 | 2025-09-01
Kansas | 2025-09-04 | 2025-06-12 |  | 2025-07-01 | 2025-07-30 | 2025-07-16 | 2025-07-30 |  |  | Link
Kentucky | 2025-09-04 | 2025-06-12 |  | 2025-06-16 | 2025-06-27 | 2025-07-10 | 2025-07-28 |  |  | Link
Louisiana | 2025-09-04 | 2025-06-11 |  | 2025-06-25 | 2025-06-27 | 2025-07-01 | 2025-07-09 | 2025-08-08 | 2025-08-15
Maine | 2025-09-04 | 2025-06-13 |  | 2025-07-10 | 2025-07-16 | 2025-07-10 | 2025-07-24 | 2025-08-22 | 2025-08-29 | Link
Maryland | 2025-09-04 | 2025-06-13 |  |  |  | 2025-07-10 | 2025-07-24 | 2025-08-08 | 2025-08-22
Massachusetts | 2025-09-04 | 2025-06-16 |  | 2025-07-01: 2025-07-11; 2025-07-09: 2025-07-31
Michigan | 2025-09-11 | 2025-06-16 |  | 2025-07-07 | 2025-07-21 | 2025-07-21 | 2025-08-04
Minnesota | 2025-09-04 | 2025-06-12 |  | 2025-06-24 | 2025-07-07 | 2025-07-14 | 2025-07-24 | 2025-08-28 | 2025-09-04 | Link
Mississippi | 2025-09-04 | 2025-06-10 |  | 2025-06-20 | 2025-06-27 | 2025-07-03 | 2025-07-17 |  |  | Link
Missouri | 2025-09-29 | 2025-06-06 |  | Rd 1: 7/3/25 Rd 2: 7/3/25 | Rd 1: 7/9/25 Rd 2: 8/15/25 | Rd 1: 7/10/25 Rd 2: 8/13/25 | Rd 1: 7/24/25 Rd 2: 8/20/25
Montana | 2025-09-04 | 2025-06-12 |  | 2025-06-13 | 2025-06-27 | 2025-07-07 | 2025-07-25
Nebraska | 2025-09-09 | [previously completed] | [previously completed] | 2025-06-26 | 2025-07-07 | 2025-06-26 | 2025-07-09
Nevada | 2025-09-04 | 2025-06-11 |  | 2025-07-14: 2025-07-08; 2025-07-24: 2025-07-17
New Hampshire | 2025-09-04 | 2025-06-16 |  | [concurrent with BOTB] | [concurrent with BOTB] | 2025-06-30 | 2025-07-18 | 2025-08-26 | 2025-09-02
New Jersey | 2025-09-04 | 2025-06-17 |  | [already open] | 2025-07-03 | 1935-06-30 | 2025-07-25
New Mexico | 2025-09-04 | 2025-06-12 |  | 2025-06-17 | 2025-06-30 | 2025-07-07 | 2025-07-21 |  |  | Link
New York | 2025-09-24 |  |  | [already open] | 2025-07-25 | 2025-07-22 | 2025-07-30
North Carolina | 2025-09-04 | 2025-06-11 |  | 2025-06-20 | 2025-07-07 | 2025-07-11 | 2025-07-30 | 2025-08-27 | 2025-09-03 | Link
North Dakota | 2025-09-04 | 2025-06-17 |  |  |  | 2025-07-03 | 2025-07-17 | 2025-08-22 | 2025-08-29
Ohio | 2025-09-04 | 2025-06-13 |  |  |  | 2025-07-28 | 2025-08-15 | 2025-08-28 | 2025-09-04
Oklahoma | 2025-09-04 | 2025-06-06 |  | 2025-07-14 | 2025-07-23 | 2025-07-14 | 2025-07-23
Oregon | 2025-09-18 | 2025-06-11 |  | 2025-06-10 | 2025-06-30 | 2025-07-18 | 2025-07-27 |  |  | Link
Pennsylvania | 2025-09-04 | 2025-06-16 | 2025-07-08 | n/a | n/a | 2025-07-18 | 2025-08-01 | 2025-08-22 | 2025-08-29
Rhode Island | 2025-09-04 | 2025-06-23 |  | n/a | n/a | 2025-07-01 | 2025-07-22
South Carolina | 2025-09-26 | 2025-06-10 | 2025-06-17 | 2025-07-11: 2025-07-07; 2025-07-30: 2025-07-24
South Dakota | 2025-09-30 | 2025-06-17 |  | n/a | n/a | 2025-07-07 | 2025-07-18 | 2025-08-28 | 2025-09-04
Tennessee | 2025-09-04 | 2025-06-12 |  | 2025-06-16 | 2025-06-24 | 2025-07-07 | 2025-07-16 | 2025-08-18 | 2025-08-25 | Link
Texas | 2025-10-27 |  |  |  |  | 2025-07-09 | 2025-07-22 | 2025-08-28 | 2025-09-04 | Link
Utah | 2025-10-03 | 2025-06-11 |  | 2025-07-07: 2025-06-27; 2025-07-16: 2025-07-10 | Link
Vermont | 2025-09-04 | 2025-06-12 |  | 2025-06-26 | 2025-07-03 | 2025-07-15 | 2025-07-25 | 2025-08-27 | 2025-09-03
Virginia | 2025-09-04 | [previously completed] | [previously completed] | 2025-06-13 | 2025-06-23 | 2025-06-27 | 2025-07-03 | 2025-08-06 | 2025-08-13
Washington | 2025-09-04 | 2025-06-16 |  | n/a | n/a | 2025-07-02 | 2025-07-23
West Virginia | 2025-09-04 | 2025-06-13 |  | 2025-06-13 | 2025-06-18 | 2025-07-10 | 2025-07-20 | 2025-08-19 | 2025-08-26
Wisconsin | 2025-09-04 | 2025-06-16 |  | 2025-06-17 | 2025-06-30 | 2025-07-17 | 2025-07-28
Wyoming | 2025-09-04 | 2025-06-10 |  | 2025-07-11 | 2025-07-20 | 2025-07-11 | 2025-07-20
Note on B2: 90 days from Public Notice dated June 6, 2025
Note on C2: Notice triggers 14 calendar day process: withing 7 days, ULFW providers must respond indicating whether they will submit evidence re service of specific locations; then they have 7 days days to submit evidence re their offerings and whether they meet technical criteria at locations. States then review and deem them served and thus ineligible for BEAD.
Note on D2: Date when state announced results of ULFW data reviews
Note on B7: Received two extensions - initially until 10/2, then until 11/21

## Leftover Funding
State | Allocation | Allocation - 2% Admin Costs | Proposed BOTB Grants | Potential Leftover Funding | % Leftover | Projected Total Leftover Funds
U.S. | 41809720792 | 40973526376.16 | 18357424071.59 | 20434765480.61 | 52.68% | 21583839738.7634
Alabama** | 1401221902 | 1373197463.96 | 479655034 | 893542429.96 | 65.07%
Alaska | 1017139672 | 996796878.56 | 791632688 | 205164190.56 | 20.58%
Arizona** | 993112231 | 973249986.38 | 511973677 | 461276309.38 | 47.4%
Arkansas | 1024303994 | 1003817914.12 | 308328088 | 695489826.12 | 69.28%
California | 1864136509 | 1826853778.82
Colorado** | 826522650 | 809992197 | 420604502 | 389387695 | 48.07%
Connecticut** | 144180793 | 141297177.14 | 7215750 | 134081427.14 | 94.89%
Delaware | 107748385 | 105593417.3 | 13374777 | 92218640.3 | 87.33%
Florida | 1169947393 | 1146548445.14 | 291117627 | 855430818.14 | 74.61%
Georgia** | 1307214371 | 1281070083.58 | 309731420 | 971338663.58 | 75.82%
Hawaii** | 149484494 | 146494804.12 | 94869000 | 51625804.12 | 35.24%
Idaho** | 583256250 | 571591125 | 436419856 | 135171269 | 23.65%
Illinois | 1040420752 | 1019612336.96 | 986254515 | 33357821.96 | 3.272%
Indiana** | 868109930 | 850747731.4 | 486309855 | 364437876.4 | 42.84%
Iowa** | 415331313 | 407024686.74 | 221282630 | 185742056.74 | 45.63%
Kansas | 451725998 | 442691478.04 | 252629600 | 190061878.04 | 42.93%
Kentucky | 1086172537 | 1064449086.26 | 376926542 | 687522544.26 | 64.59%
Louisiana** | 1355554553 | 1328443461.94 | 498296587 | 830146874.94 | 62.49%
Maine** | 271977723 | 266538168.54 | 48369285 | 218168883.54 | 81.85%
Maryland | 267738401 | 262383632.98 | 78106623 | 184277009.98 | 70.23%
Massachusetts | 147422464 | 144474014.72 | 18654558 | 125819456.72 | 87.09%
Michigan** | 1559362479 | 1528175229.42 | 906927582 | 621247647.42 | 40.65%
Minnesota** | 651839368 | 638802580.64 | 391611699 | 247190881.64 | 38.7%
Mississippi** | 1203561563 | 1179490331.74 | 567298770 | 612191561.74 | 51.9%
Missouri | 1736302708 | 1701576653.84 | 792326180 | 909250473.84 | 53.44%
Montana** | 628973799 | 616394323.02 | 308194874 | 308199449.02 | 50%
Nebraska | 405281070 | 397175448.6 | 43844548 | 353330900.6 | 88.96%
Nevada** | 416666230 | 408332905.4 | 174711767 | 233621138.4 | 57.21%
New Hampshire** | 405281070 | 397175448.6 | 19304336 | 377871112.6 | 95.14%
New Jersey | 263689549 | 258415758.02 | 63551463 | 194864295.02 | 75.41%
New Mexico | 675372312 | 661864865.76 | 432974698 | 228890167.76 | 34.58%
New York | 664618251 | 651325885.98 | 391097992 | 260227893.98 | 39.95%
North Carolina | 1532999481 | 1502339491.38 | 408511175 | 1093828316.38 | 72.81%
North Dakota | 130162815 | 127559558.7 | 6770073 | 120789485.7 | 94.69%
Ohio | 793688108 | 777814345.84 | 242397568 | 535416777.84 | 68.84%
Oklahoma** | 797435691 | 781486977.18 | 654972190 | 126514787.18 | 16.19%
Oregon** | 688914932 | 675136633.36 | 621365070 | 53771563.36 | 7.965%
Pennsylvania** | 1161778272 | 1138542706.56 | 790729316 | 347813390.56 | 30.55%
Rhode Island | 108718821 | 106544444.58 | 16137983 | 90406461.58 | 84.85%
South Carolina | 551535983 | 540505263.34 | 41358389 | 499146874.34 | 92.35%
South Dakota | 207227524 | 203082973.52 | 72816060 | 130266913.52 | 64.14%
Tennessee | 813319680 | 797053286.4 | 203311189 | 593742097.4 | 74.49%
Texas | 3312616455 | 3246364125.9 | 1271233724 | 1975130401.9 | 60.84%
Utah | 317399742 | 311051747.16 | 231284902 | 79766845.16 | 25.64%
Vermont** | 228913019 | 224334758.62 | 120113540 | 104221218.62 | 46.46%
Virginia** | 1481489573 | 1451859781.54 | 545170411 | 906689370.54 | 62.45%
Washington** | 1227742066 | 1203187224.68 | 850259872 | 352927352.68 | 29.33%
West Virginia** | 1210800970 | 1186584950.6 | 624455662 | 562129288.6 | 47.37%
Wisconsin | 1055823574 | 1034707102.52 | 691929792 | 342777310.52 | 33.13%
Wyoming | 347877921 | 340920362.58 | 198442261 | 142478101.58 | 41.79%
District of Columbia | 100694787 | 98680891.26 | 996099 | 97684792.26 | 98.99%
American Samoa | 37564828 | 36813531.44 | 8386765.59 | 28426765.85 | 77.22%
Guam | 156831734 | 153695099.32 | 1820291 | 151874808.32 | 98.82%
Northern Mariana Islands | 80796709 | 79180774.82 | 31365216 | 47815558.82 | 60.39%
Puerto Rico | 334614152 | 327921868.96
U.S. Virgin Islands | 27103241 | 26561176.18
Note on D3: Down from initial projected allocation of $530743198
Note on D4: Initial allocation: $766065522 Revised as of 9/25: $776848805 Cited figure as of 10/8 (includes negotiated awards for areas that didn't receive bids initially)
Note on D5: Revised down from $512129676 in initial data release (figure cited as of 9/15/25)
Note on D8: Up from $409M in Draft FP
Note on D9: Slight revision down from $7216501 (figured cited is as of 9/25)
Note on D12: Up from $309602816 in draft FP
Note on D13: Down from $95659050 in draft FP
Note on D14: Slight revision up from initial figure of $436151356 (data cited in sheet as of 9/16/25)
Note on D15: Initial projected allocation: $990645134
Note on D21: No change from draft to submitted FP
Note on D24: Increased from $919106714 in initial materias released with draft FP to $924895073. Cited figure is as of 9/30/25 (as submitted to NTIA)
Note on D25: Up from $377046314 in draft FP
Note on D26: Up from $567165372 in draft FP
Note on D28: Down from $403758268 in draft FP
Note on D29: Revised down from $56522960 in initial draft doc released
Note on D30: Revised up from $169749805 in initial data release. Cited figure citation: https://www.osit.nv.gov/siteassets/home/high-speed-nevada-initiative-phase-iii-list-of-last-mile-awardees.pdf
Note on D31: Down from $19305222 in draft FP
Note on D37: Down from $277114388 in initial version of deployment projects file
Note on D38: Initial proposed allocation: $493318563 Updated as of 9/24: $655881242 Cited figure as of 10/3
Note on D39: Revised up from $620728287
Note on D40: Down from $793494747 in draft FP
Note on D46: User Name:
Note on D47: Initial projected allocation: $118993040 Subsequent revision to $120113540 Cited figure as of 9/22
Note on D48: No change from draft to submitted FP; downward revision as of 9/18 from $613277638
Note on D49: Up from $849894572 in draft FP
Note on D50: Down from $624671276 in draft FP Submitted data: https://broadband.wv.gov/news/governor-morrisey-announces-final-proposal-to-connect-74000-with-high-speed-internet/